## Slide 1
Evaluation (01/04/2018)
Feasibility (01/10/2017)
Discovery (26/01/2018) * time allowed for January Exams
Delivery (16/02/2018)
Demonstration Event (03/05/2018)
(2/5) Investigate video processing techniques for facial and object detection
(2/2) Investigate best available software for video processing
(1/7) Investigate unsupervised learning models for anomaly detection
(1/3) Investigate best software for providing machine learning models
(5) Develop a video processing PoC with investigated software
(5) Develop a machine learning PoC with investigated software
(3) Develop a messaging service layer for service communication PoC
(2) Develop a web user interface PoC
(3) Develop Continuous Integration infrastructure and production infrastructure capabilities
(3) Requirement: Build test cases to deem success of system
(4) Feature: Extrapolate necessary and useful features from video processing service
(3) Feature: Configure known users for facial recognition in video processing service
(7) Feature: Machine learning model combination exploring for best results
(3) Feature: Build and tune machine learning models for behaviour classification
(5) Feature: Display recorded event statistics in the web user interface
(7) Requirement: Develop load testing capability to allow system benchmarking
(2) Feature: Allow multiple cameras to simultaneously stream
(9) Feature: Allow communication to camera to store video if anomaly detected
(4) Feature: Alert sending on anomaly detection
Minimum Viable Product (23/03/2018)
(3) Use Case: Run system against test cases collecting meta data
(5) Evaluate: Accuracy of system analysing final machine learning configuration
(4) Evaluate: Performance of system in processing video and events
(4) Evaluate: Storage required to provide anomaly detection service
(5) Requirement: Project Poster
Key:
(Number) : The complexity points estimated for the task